## Sheet1
|  |  |  | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
Sub system | Task | Sub Task | Assigned people | 16/02 | 23/02 | 02/03 | 09/03 | 16/03 | 23/03 | 30/03 | 06/04 | 13/04 | 20/04 | 27/04 | 04/05 | 11/05 | 18/05 | 25/05 | 01/06
Cathode
| PDR |  | All |  |  | DUE ON 8TH
Insert Options
Mechanical design
Power system
| Manufacture Prep | [7 empty] | DUE ON 29TH
Parts Manufacture
Assembly
Test
Anode
| PDR | [7 empty] | DUE ON 29TH
Manufacture Prep
Parts Manufacture
Assembly
Magnetics
| PDR | [7 empty] | DUE ON 29TH
Manufacture Prep
Parts Manufacture
Assembly